## Slide 1
PROJECT DRISHTI
Kickoff: Data, Analytics & Reporting Transformation
Prepared for Bharadwaj Consumer Products Ltd, by Northlane Analytics
Wednesday 11 February 2026, 15:00–16:00 IST
Board room “Nashik”, 4th Floor, Andheri East office (with remote joiners)
Presented by Ananya Krishnan, Engagement Lead
Deck prepared 10/02/2026
Bharadwaj Consumer Products Ltd | Confidential, Client Use Only | Project Drishti, Kickoff Deck v3
1
Notes: Venue is the Nashik board room, 4th floor, Andheri East. The wifi in that room drops constantly - if the screen share fails, switch to a hotspot rather than fighting the office network for ten minutes like we did in the dry run. Marijke van der Berg dials in from Amsterdam and is only on for the first twenty minutes (10:30-10:50 her time), so do not schedule her questions for late in the hour - front-load objectives and the plan while she is still on the line. Recording will sit on the site for ninety days per the usual policy, mention that once at the start and do not bring it up again.

## Slide 2
Agenda
Engagement Objectives
Plan on a Page
Current State: As-Is Landscape
Problem Statement
Reporting Scope
Approach: Workstreams
Team
Ways of Working & Governance
Risks & Assumptions
Next Steps
Questions
60 minutes, hard stop.
Marijke joins for the first 20 minutes only.
Kindly hold detailed questions on any one slide until the end, or we will not get through the pack otherwise.
Bharadwaj Consumer Products Ltd | Confidential, Client Use Only | Project Drishti, Kickoff Deck v2
2
Notes: Hard stop at 60 minutes, Rajeev has another call at four. If we are behind by the As-Is section, cut Ways of Working, not the plan slide or the reporting scope slide - those two are what Rajeev actually remembers from any deck of ours. Do not read this out loud, but the version on screen today replaces the copy that went out on Friday - only slide four changed since then, nothing else did, so do not re-litigate the rest of the pack if someone says it looks different from what they printed.

## Slide 3
Engagement Objectives
Building on our conversations with Rajeev and Shalini over the past fortnight, this is what we are here to deliver.
Establish a single, trusted source of sales and Distributor reporting for BCPL, replacing today's mix of OBIEE reports and shadow Excel trackers
  One version of the truth for Primary and Secondary sales, by distributor, by SKU, by region
  Numbers that tie back cleanly across Sales Ops, Finance and the Klarissen Group pack
Modernise the reporting stack onto Power BI, sunsetting OBIEE and cutting the manual Excel effort
  12 dashboards scoped for go-live (full list on the Reporting Scope slide)
  A considered migration path for the reports Priya's team actually uses today, not just everything sitting in the catalogue
Build a defensible, well-governed data foundation in the warehouse that BCPL and Klarissen can both stand behind
  Documented lineage from ORION through ODI into BCPL_EDW
  A data quality baseline the business agrees with, not just IT
Deliver all of the above by go-live, GO-LIVE 15 SEPTEMBER 2026, with minimal disruption to the daily sales cycle
Bharadwaj Consumer Products Ltd | Confidential, Client Use Only | Project Drishti, Kickoff Deck v3
3
Notes: If Vikram pushes back that stockist-level reporting is not called out by name, remind him distributor-level reporting is covered under objective one - he uses his own word for the same thing, do not rename the bullet on screen just for him, it will only confuse Priya and Ritwik who use different words again. Keep this slide to two minutes, it is scene setting, not the sale - the sale already happened, the SOW is signed.

## Slide 4
PROGRAMME TIMELINE
Plan on a Page
Phase | Milestone | Dates
Phase 1 – Discovery & Variance Root Cause | Discovery | 11-Feb-2026 to 27-Mar-2026
Phase 1 – Discovery & Variance Root Cause | Variance Root-Cause Sprint | 09-Mar-2026 to 08-May-2026
Phase 2 – Remediation & Warehouse Rebuild | Data Quality Assessment | 04-May-2026 to 19-Jun-2026
Phase 2 – Remediation & Warehouse Rebuild | Remediation Build | 15-Jun-2026 to 25-Sep-2026
Phase 3 – Power BI Build & Testing | Dashboard Build | 03-Aug-2026 to 09-Oct-2026
Phase 3 – Power BI Build & Testing | UAT | 10-Aug-2026 to 28-Aug-2026
Phase 4 – Cutover, Go-Live & Hypercare | GO-LIVE | 15 SEPTEMBER 2026
GO-LIVE
15 SEPTEMBER 2026
Tuesday
31 weeks, kickoff to go-live, across four phases.
Full cutover and hypercare plan to follow in Phase 4. OBIEE is targeted for decommission 90 days after go-live.
Bharadwaj Consumer Products Ltd | Confidential, Client Use Only | Project Drishti, Kickoff Deck v3
4
Notes: THE ONLY DATE THAT MATTERS TO RAJEEV ON THIS WHOLE DECK: Tuesday 15 September 2026. Say it exactly like that on the call, not 'mid-September', not 'Q3 2026'. If Shalini asks whether the UAT window (10 to 28 August) is realistic given everything scheduled ahead of it, the honest answer is that it is tight and we have said so internally already - do not volunteer that on the call today, answer only if asked directly. Do not read out the phase boundaries in detail. They overlap on purpose at this stage - nobody has reconciled them line by line yet, that happens once discovery findings land.

## Slide 5
SECTION 1
Current State: As-Is Landscape
Bharadwaj Consumer Products Ltd | Confidential, Client Use Only | Project Drishti, Kickoff Deck v3
5

## Slide 6
As-Is Landscape: Systems Overview
System | What it does | Platform
ORION | Core order-to-cash OLTP: orders, invoices, credit notes, schemes. Built 2009. | Oracle Database 19c; Oracle Forms/Reports, partially re-fronted in ADF
ODI | Extracts and loads ORION data into the warehouse on a nightly batch cycle | Oracle Data Integrator 12c
BCPL_EDW | Central sales and distribution warehouse, star schema | Oracle Database 19c
OBIEE | Legacy BI / reporting layer; 41 catalogue reports, a small number actually used | Oracle BI EE 11g; RPD last touched 2019
Excel | The de facto reporting layer for Finance and Sales Ops; Distributor and scheme numbers often re-keyed by hand | Shadow workbooks, manual reconciliation
Power BI | Target reporting platform for Project Drishti, replacing OBIEE and reducing the Excel dependency | Microsoft Power BI
Bharadwaj Consumer Products Ltd | Confidential, Client Use Only | Project Drishti, Kickoff Deck v3
6
Notes: Ani (Aniruddh Deshpande) is not on this call today, patching commitment, Rajeev is chasing him for the next session. He was there when ORION was originally built back in 2009 and is genuinely the only person who remembers why some of it is the way it is - nobody else in the room today can go deep on ORION history, so park any vintage question for the OLTP discovery session rather than guessing on this call.

## Slide 7
AS-IS LANDSCAPE, CONTINUED
Current State: Known Pain Points
ORION was built in 2009 by a vendor relationship that ended in 2014; institutional knowledge now sits with a handful of people
  Original functional specifications are not readily available
  Fifteen-plus years of schema changes are not fully documented anywhere central
Nightly batch loads move data from ORION into the warehouse; the business only sees yesterday's numbers, never today's
  Sales Ops, Finance and BI cannot self-serve; every ad-hoc question becomes a ticket or an email chain
  Change requests to the load queue behind ORION support work, not warehouse priorities
OBIEE is fifteen-year-old technology; the RPD has not been touched since 2019
  Only a small number of the 41 catalogue reports are actually opened month to month
  Nobody formally owns retiring the reports that are not used
  Report definitions live in people's heads, not in a document
Excel has become the real reporting layer, in practice
  Finance and Sales Ops each maintain their own shadow workbooks
  Numbers get rekeyed by hand between systems, more than once a month, per team
Reporting is fragmented across systems and teams; data recieved from ORION does not always match what people see downstream
Nobody today owns “the number” end to end, across ORION, ODI and OBIEE
None of this is new to BCPL. It has been true for years, and it is getting worse as the business grows, not better -
Bharadwaj Consumer Products Ltd | Confidential, Client Use Only | Project Drishti, Kickoff Deck v3
7
Notes: This slide is deliberately the busy one - it is doing the job of making the case for the programme, resist tidying it live on screen, the mess is the point today. If someone asks for a number on how bad the data actually is, we do not have one yet - that is the whole point of discovery. Say that plainly rather than guessing at a figure to sound prepared, a wrong number said out loud in this room will follow us for months.

## Slide 8
Problem Statement
Sales Ops, Finance and the Klarissen Group pack routinely see different numbers for the same period, and reconciling them takes days, not hours
There is no single, governed definition of “the number”. Primary sales, Secondary sales and scheme figures get quoted loosely and interchangeably across teams
Data recieved from ORION does not always match what shows up in OBIEE, or in the Excel trackers Finance and Sales Ops each keep on the side
Nobody can say, with confidence, today, how much of the reported revenue would survive a detailed line-by-line audit
The current stack (ORION, through ODI, into OBIEE) was built for a much smaller business and has not kept pace with BCPL's growth or with Klarissen's group reporting needs
This is costing real management time every month end, and it is not getting easier -
This, in one line, is why Project Drishti exists.
Bharadwaj Consumer Products Ltd | Confidential, Client Use Only | Project Drishti, Kickoff Deck v3
8
Notes: Shalini will ask, in some form, whether we can tie the dashboard back to the trial balance. The honest answer today is that we don't know yet, we have not looked at a single row. Say that plainly rather than reassuring her - she will trust 'we don't know yet, but here is how we will find out' far more than a confident guess. Do not name a rupee figure on this call. We do not have one, and we should not invent one to fill a silence.

## Slide 9
12 DASHBOARDS IN SCOPE FOR GO-LIVE
Reporting Scope
ID | Dashboard | Primary Data
D01 | Primary Sales Performance | FACT_INVOICE_LINE
D02 | Secondary Sales Coverage | FACT_SECONDARY_SALES
D03 | Distributor Scorecard | FACT_INVOICE_LINE
D04 | Scheme Effectiveness | FACT_INVOICE_LINE + DIM_SCHEME
D05 | Stock and Despatch | FACT_INVOICE_LINE
D06 | Order Fulfilment and Fill Rate | FACT_ORDER_LINE
D07 | Revenue Reconciliation | FACT_INVOICE_LINE
D08 | GST and Tax Summary | FACT_INVOICE_LINE + DIM_TAX_RATE
D09 | Product Mix and Contribution | FACT_INVOICE_LINE
D10 | Sales Rep Productivity | FACT_INVOICE_LINE + DIM_SALESREP
D11 | Credit and Receivables Exposure | AR_OPEN_ITEM extract
D12 | Executive Summary (Group View) | Aggregate, all of the above
12
DASHBOARDS
D01–D12, in scope for go-live per the SOW.
Sequencing and dashboard-by-dashboard wireframes are worked out with each business owner during the Dashboard Build phase.
Bharadwaj Consumer Products Ltd | Confidential, Client Use Only | Project Drishti, Kickoff Deck v3
9
Notes: Rajeev will ask how many dashboards he is getting. Answer: twelve, D01 through D12, exactly as listed here. That is one of only two numbers he retains from this entire deck - the other is the go-live date on slide four. Do not get pulled into sequencing which of the twelve get built first, that is a conversation for the dashboard workshops later in the programme, not for kickoff.

## Slide 10
SECTION 2
Our Approach
Bharadwaj Consumer Products Ltd | Confidential, Client Use Only | Project Drishti, Kickoff Deck v3
10

## Slide 11
Workstreams
Workstream | Focus | Lead
WS1 – Data & Variance Root Cause | Inventory every source of a sales number, define terms precisely, profile the actual tables, and trace one period end to end from ORION through to the report | Karthik Subramanian
WS2 – Data Quality | Baseline and improve completeness, validity, consistency, uniqueness and timeliness of core sales data | Neha Gokhale
WS3 – Dashboard Design & Build | Design and build the Power BI dashboards, retiring OBIEE reports as we go | Ritwik Ghosh
WS4 – Change, UAT & Cutover | User acceptance testing, training and cutover planning | Ananya Krishnan
WS5 – Programme Governance | Steering, RAID management and status reporting | Ananya Krishnan
Bharadwaj Consumer Products Ltd | Confidential, Client Use Only | Project Drishti, Kickoff Deck v3
11
Notes: Karthik's workstream (root cause and data architecture) is the one everything else waits on. If time runs short on the call, protect his slot and cut short the Ways of Working slide instead - governance can be sent round as a follow-up note, discovery approach cannot.

## Slide 12
The Team
DRAFT: photos pending
Bharadwaj Consumer Products Ltd
PHOTO PENDING
Rajeev Menon
CIO, Executive Sponsor
PHOTO PENDING
Shalini Iyer
Head of Finance Systems, Business Sponsor
PHOTO PENDING
Vikram Sethi
National Sales Operations Manager
PHOTO PENDING
Priya Nair
BI Analyst
PHOTO PENDING
Farida Contractor
ODI / ETL Lead
PHOTO PENDING
Aniruddh Deshpande
Senior Oracle DBA
Klarissen (Sponsor)
PHOTO PENDING
Marijke van der Berg
Group CFO, Klarissen Group N.V.
Northlane Analytics
PHOTO PENDING
Ananya Krishnan
Engagement Lead
PHOTO PENDING
Karthik Subramanian
Data Architect
PHOTO PENDING
Ishaan Bhatt
Analytics Engineer
PHOTO PENDING
Neha Gokhale
Data Quality Lead
PHOTO PENDING
Ritwik Ghosh
BI Developer
PHOTO PENDING
Sneha Pillai
Business Analyst
Team composition as at SOW signature (28-Jan-2026): 6 named Northlane Analytics consultants plus 2 offshore developers (join for the build phase). Photos pending from HR only, placeholders shown above.
Bharadwaj Consumer Products Ltd | Confidential, Client Use Only | Project Drishti, Kickoff Deck v3
12
Notes: Photos are still pending from HR as of this morning, do not apologise for the placeholders more than once. Ani (Aniruddh Deshpande) is not on today's call either, patching commitment - Rajeev is chasing him for the next session. On the Northlane Analytics side, Ishaan starts next week and Neha comes in around the quality assessment, per Ananya's own line to the room today. Meghna Rao (BCPL, Data Quality Analyst) is not shown on this slide; she formally joins once the Data Quality Assessment phase opens in May, and will not be on most calls before then.

## Slide 13
Ways of Working & Governance
Forum | Frequency | Attendees | Mode
Steering Committee | Monthly | Rajeev (Chair), Shalini, Vikram, Marijke, Ananya, Karthik | Video call
Core Working Session | Weekly, Tuesdays 16:00 IST | Farida, Karthik, Ishaan, Priya, Ani, Ananya, Sneha | Video call
Status Report | Weekly, Friday | Circulated to the steering committee distribution list | Email
Workshops | As required, per workstream | Workstream leads plus SMEs | Andheri office (“Nashik”) or video call
One issue, one owner, one due date, tracked centrally in the action tracker, not in someone's inbox
Every status call reviews open actions before anything new is discussed
Escalate early, not late. Rajeev wants to hear about a problem before the steerco, not in it
Nothing touches production between now and the FY26 close on 31-Mar-2026
Bharadwaj Consumer Products Ltd | Confidential, Client Use Only | Project Drishti, Kickoff Deck v3
13
Notes: Steerco membership is fixed: Rajeev chairs, Shalini, Vikram, Marijke, Ananya and Karthik sit on it. Sneha takes the minutes and is not formally a member, though she is on every single call so people tend to assume she is - do not correct anyone on this in the room, it does not matter. Get the steerco invites out for the whole year in one go, not month by month, Rajeev asked for that specifically.

## Slide 14
Risks & Assumptions
Risk / Assumption | Mitigation | Owner
Legacy system knowledge is concentrated in a small number of people | Document as we go; do not rely on tribal memory alone | Karthik / Ani
The nightly batch load has a fixed business-availability window; any change to it adds elapsed time | Any remediation is measured on DEV before it goes near PROD | Farida / Karthik
Reporting scope depends on Klarissen budget approval each planning cycle | Track as a standing dependency in the steerco pack | Ananya
Assumption: BCPL Sales Ops and Finance will nominate UAT testers and be available through August | Confirm nominees by end of Discovery | Shalini / Vikram
Assumption: ORION remains stable and unchanged through the Remediation Build phase | Track any planned ORION release as a programme risk | Farida
Bharadwaj Consumer Products Ltd | Confidential, Client Use Only | Project Drishti, Kickoff Deck v3
14
Notes: If Farida raises the load window as a risk, acknowledge it warmly and do not commit to a number - nothing has been measured yet, that is deliberately the whole point of discovery. Same answer if anyone asks how bad the data quality actually is: we genuinely do not know, and saying so is the right answer today, not a weak one.

## Slide 15
Next Steps
Action | Owner | Due
Circulate final kickoff pack and minutes | Sneha Pillai | 12-Feb-2026
Confirm workstream leads and finalise team allocation | Ananya Krishnan | 18-Feb-2026
Begin OLTP discovery sessions with the ORION / DBA team | Karthik Subramanian | Week of 16-Feb-2026
Raise access requests for ORION and BCPL_EDW read-only accounts | Farida Contractor | 20-Feb-2026
Set up the weekly working session and steering committee invites for the year | Sneha Pillai | 13-Feb-2026
Confirm UAT tester nominees for August | Shalini Iyer / Vikram Sethi | TBC
Kindly note: as such, this list will only grow once discovery starts properly. Treat it as the opening list, not the whole tracker.
Bharadwaj Consumer Products Ltd | Confidential, Client Use Only | Project Drishti, Kickoff Deck v3
15
Notes: Ananya owes Shalini and the room a written recap. Sneha's note needs to go out quickly, by tomorrow at the latest - Shalini chases fast if it slips, first with a gentle reminder, then with a much shorter one. Do not let the note wait for the corrected deck to be formatted, send the notes and the deck can follow within the hour if needed.

## Slide 16
Thank You
One number, one source of truth, by 15 September 2026.
Questions and follow-ups: Ananya Krishnan, ananya.krishnan@northlaneanalytics.example
Bharadwaj Consumer Products Ltd | Confidential, Client Use Only | Project Drishti, Kickoff Deck v3
16
Notes: Standard close - thank the room, remind them Sneha sends the notes and the corrected pack today, and that the first working session is next Tuesday at 16:00 IST.

## Slide 17
SYNTHETIC — generated for internal demo. No real entity depicted.