## Slide 1
PROJECT DRISHTI | BHARADWAJ CONSUMER PRODUCTS LTD
Steering Committee
Tuesday, 22 September 2026, 15:00-15:45 IST | MS Teams
Bharadwaj Consumer Products Ltd | Klarissen Group N.V. | Northlane Analytics
Circulated to: Rajeev Menon, Shalini Iyer, Vikram Sethi, Karthik Subramanian, Ananya Krishnan, Sneha Pillai
cc: van der Berg, Marijke (Klarissen Group N.V.) | Tan, Wei Lin (Klarissen Group N.V.)
Confidential - Steering Committee Distribution Only
Bharadwaj Consumer Products Ltd | Confidential - Steering Committee Distribution Only
1
Notes: Chair: Rajeev Menon. This is the 22-Sep pack, prepared off the 18-Sep tracker save (there were two versions floating around last week, Shalini flagged this on the call - confirm we are all on v7 before item 2).
Marijke is on for the full 45 minutes (11:30-12:15 CEST). Wei Lin is not on this call, she is cc'd on the pack only, so do not address her directly or wait on her for anything.
Do not open with the date. Ananya's line is to say up front this is NOT a build problem, it is the Klarissen group close blackout - say that before anyone asks, it lands better.

## Slide 2
22 SEPTEMBER 2026 · 45 MINUTES
Agenda
• The plan and the go-live date
  – Klarissen group close blackout and the revised cutover shape
• Variance register
  – Closed items, then open items
  – Credit note position (VAR-005) - taken as a sub-item at Marijke's request
• Reporting scope for go-live
  – Dashboards confirmed, funding position
• Any other business
  – UAT window
  – Actions
v2 - updated 21-Sep after dry-run w/ Rajeev
Bharadwaj Consumer Products Ltd | Confidential - Steering Committee Distribution Only
2
Notes: Three items only, keep to time, Rajeev has a hard stop at quarter to (another call). If we run over, drop the AOB detail and just read the actions.
Reminder for whoever is sharing screen: the pack is also on the invite, some of them will be following on their own laptop rather than the shared screen, do not assume everyone is looking at the same slide at the same time.

## Slide 3
1
The Plan and the Go-Live Date
Bharadwaj Consumer Products Ltd | Confidential - Steering Committee Distribution Only
3
Notes: Lead with: this is not a build problem. Say that sentence before Rajeev or Shalini can ask what has gone wrong again - it changes the tone of the next six minutes.

## Slide 4
Programme Status at a Glance
Overall programme status: GREEN
Workstream | Lead | RAG | Comment
Discovery & Root-Cause | Karthik Subramanian | G | Closed out; findings carried into remediation build.
Data Quality & Remediation | Neha Gokhale | A | Four of eight variance register items still open.
Dashboard Build | Ritwik Ghosh | G | Tracking to the confirmed 12-Nov date.
UAT & Cutover Readiness | Ananya Krishnan | A | October window agreed in principle; tester nominations TBC.
Change Mgmt & Hypercare | Sneha Pillai | G | Plan agreed through to 11-Dec close of hypercare.
Status as reported to this committee. Detail by item follows.
Bharadwaj Consumer Products Ltd | Confidential - Steering Committee Distribution Only
4
Notes: DO NOT read the Dashboard Build row out as a flat green if Karthik or Shalini pushes on it. Ritwik's team is basically two reports behind where the plan said they would be this week; it is being smoothed over for this slide because the two dashboards that came back in (D04, D11) sit on the existing model, so it does not move the date, only the workload. If asked directly, say amber verbally and move on.
Separately, and this is important: Shalini has NOT agreed the November resourcing for UAT. She asked, in the last steerco, for this to be minuted seperately rather than folded into a green row. If she raises it, do not argue, just confirm it will be tracked as an open item, not as agreed capacity. This is basically the same three people every cycle and she knows it.

## Slide 5
The Plan and the Go-Live Date
• This is not a build or a data problem. It is a Group calendar constraint.
• The Klarissen Group close blackout runs 26 October to 06 November (CET). No operating company may cut over inside that window.
• The cutover therefore sits entirely on the clean side of the blackout, once UAT has run.
Milestone | Date
Cutover weekend | Saturday 7 - Sunday 8 November 2026
Historical reload window | Monday 9 - Wednesday 11 November 2026
Business go-live | Thursday 12 November 2026
Hypercare ends | Friday 11 December 2026
No change to commercials - the revised plan stays inside the capped fee. Revised milestone slide to follow in writing on 22/09.
Bharadwaj Consumer Products Ltd | Confidential - Steering Committee Distribution Only
5
Notes: If Rajeev asks 'since when do we know this' - the blackout is a standing Group calendar item, not new information, it is the UAT timeline catching up with a constraint that was always there.
Master data freeze for distributor/territory records begins the Friday evening before the cutover weekend (6-Nov). This is an operational detail, not yet in a formal freeze note - Vikram will ask about it, tell him a freeze note is coming separately, do not get into territory-mapping specifics on this call.
If Shalini raises the October close overlapping the reload week: the reload does not restate any values, it is the same source rows going back in. Do not let that turn into a wider reconciliation debate on this call, park it.

## Slide 6
2
Variance Register
Eight items known. Four closed, four open.
Bharadwaj Consumer Products Ltd | Confidential - Steering Committee Distribution Only
6
Notes: Walk closed items first, then open. Do not let the credit note conversation start before the closed items are done, Marijke will try to jump straight to it, hold her off politely.

## Slide 7
Variance Register - Status Summary
ID | Title | Status | FY26 Impact (INR)
VAR-001 | Q1 revenue overstatement (cancelled lines counted as revenue) | Closed | 4.20 Cr
VAR-002 | Month-end boundary drift | Closed | -
VAR-003 | Scheme discount double-count | Open | 1.70 Cr
VAR-004 | Distributor reassignment duplicates | Open | -
VAR-005 | Credit notes absent from warehouse | Open | 3.10 Cr (validated)
VAR-006 | GST rate change mishandled | Closed | -
VAR-007 | Late-arriving SKUs (volume item, no rupee value in register) | Open | -
VAR-008 | Feb duplicate load | Closed | 2.90 Cr
TOTAL | 4 closed / 4 open | 13.85 Cr | 8.40 Cr closed / 5.45 Cr open
Bharadwaj Consumer Products Ltd | Confidential - Steering Committee Distribution Only
7
Notes: Numbers as they stand in the tracker, version 7, saved 18-Sep. Shalini already flagged on the invite that there were two versions floating around last week - confirm out loud that everyone is looking at v7 before you start, it saves a detour later.
Arithmetic check someone will do in their head: 1.70 + 0.65 + 3.11 = 5.46, but the summary says 5.45. That is because the summary sheet rounds the VAR-005 figure to 3.10 while the detail sheet carries 3.11 - the one-lakh gap is a rounding artefact between two tabs of the same workbook, not a new error. This is already an open action on Ananya (fix the tracker), do not try to reconcile it live on the call, and do not let Rajeev wave it away with 'let's not boil the ocean' either, Shalini will push back on that exact point, let her.
VAR-004 workstream lead is Ishaan Bhatt. Do not editorialise on that beyond confirming who to contact if asked.

## Slide 8
Open Items in Focus: VAR-003 and VAR-005
• VAR-003 – Scheme discount double-count
  – Owner: Aniruddh Deshpande. FY26 impact INR 1.70 Cr. Status unchanged since the last steering committee.
  – Root cause is source-side, not in the ETL. A finance procedure inside ORION rewrites the scheme discount amount; the mapping itself is not at fault.
  – The stored procedure walkthrough has been circulated separately for anyone who wants the detail. No committed close date is being given today.
• VAR-005 – Credit notes absent from warehouse
  – Owner: Shalini Iyer. Open since 24-Apr-2026.
  – Validated FY26 impact: INR 3.11 Cr, across 1,206 documents (rate difference and off-invoice adjustment types only). Validated against the FY26 trial balance on 21-Jul-2026.
  – Still open, five months on. Raised at Group level as part of the credit note escalation.
  – Ask: resolve the ownership question (who fixes it, not just who reports it) before Klarissen's 31-Dec year end.
Bharadwaj Consumer Products Ltd | Confidential - Steering Committee Distribution Only
8
Notes: Marijke will ask what the plan is for VAR-005. Do not give her a plan or a date on this call. The line is: options will come back before the next steering committee, not today. She wants a date and an owner for the fix, not options - acknowledge that directly rather than pretending the ask was for something softer.
Do not describe, hint at, or speculate on how credit notes might eventually be handled inside Power BI or the semantic model. That is not decided and is explicitly not for this room. If pushed, say Finance and architecture will bring a recommendation back.
If asked whether VAR-005 is in the audit file: it is in the variance register, and the register goes to the audit call, but Marijke has already made clear that is not the same thing as being IN the audit file itself - Rajeev has an action to confirm that separately, do not claim it is already done.
FY26 figure only. The FY27 position is not yet available; Finance has not committed a date for it. Do not offer one on their behalf.

## Slide 9
3
Reporting Scope for Go-Live
Bharadwaj Consumer Products Ltd | Confidential - Steering Committee Distribution Only
9
Notes: Confirm nine, at go-live, on the twelfth. Say the number before anyone asks for it.

## Slide 10
Dashboards Confirmed for Go-Live
Nine dashboards, live on 12 November.
ID | Dashboard
D01 | Primary Sales Performance
D03 | Distributor Scorecard
D04 | Scheme Effectiveness (reinstated, August)
D05 | Stock and Despatch
D06 | Order Fulfilment and Fill Rate
D07 | Revenue Reconciliation
D09 | Product Mix and Contribution
D11 | Credit and Receivables Exposure (reinstated, August)
D12 | Executive Summary (Group view)
D04 and D11 reinstated at Klarissen's request following the credit note escalation and the scheme discount work, funded from the Phase 2 budget line released in August. D11 is built on receivables ageing from the AR open-item extract.
Bharadwaj Consumer Products Ltd | Confidential - Steering Committee Distribution Only
10
Notes: If someone (probably Vikram) asks if secondary sales coverage is in the nine: it is not. He sees his secondary sales the same way he does today, this does not change on the twelfth. Take that conversation offline, do not get drawn into his North distributor numbers on this call, they are not on this agenda.
The two reinstated dashboards sit on the existing data model, this is build effort only, it is not new plumbing, and it does NOT move the go-live date. Karthik will confirm this if asked. Ritwik already has wireframes for both from August so the team is not starting cold.
Confirm: this is nine AT go-live on the twelfth, not nine by the end of hypercare. Wei Lin is not on this call but she will pick at that exact distinction when she reads the pack, so get the wording right now rather than clarifying by email later.

## Slide 11
Programme Risks and Open Items - Full Detail
• Delivery
  – D04 / D11 build effort lands on the existing DRISHTI_SALES model; no new plumbing, does not move the 12-Nov date, but it is additional load on Ritwik's team in the same window as the rest of the build.
  – Dashboard build workstream reported Green this cycle; watching closely, revisit next cycle if slippage shows up.
• Data / Variance
  – VAR-003 (scheme discount double-count): no committed close date. Source-side, owned by Aniruddh Deshpande. Karthik and Ani have not yet agreed a joint position.
  – VAR-004 (distributor reassignment duplicates): open, workstream lead Ishaan Bhatt.
  – VAR-005 (credit notes): validated at INR 3.11 Cr, open since April. See separate slide, flagged red in the register.
  – VAR-007 (late-arriving SKUs): a volume item, no rupee value carried in the register; it stays a register line, not a board pack rupee figure.
• Resourcing
  – UAT draws testers from Finance, Sales Ops and the BI team. Shalini has flagged, more than once now, that it is basically the same three people from her side every cycle.
  – November UAT resourcing is NOT yet agreed by Finance. Separate action, do not treat as closed.
• Governance / Audit
  – Action on Rajeev to confirm the variance register position is reflected in the Group audit file, not only the internal register. Marijke has asked for this in writing.
  – Credit note number (VAR-005) requested for the audit file seperately from the register - these are being treated by Group Finance as two different things.
• Commercial
  – No change to commercials from the revised cutover shape. The plan stays inside the capped fee as it stands today.
• Timing
  – FY26 credit note figure (3.11 Cr) is an FY26-only number. The FY27 position has not been given a date by Finance yet. As such, do not quote one.
  – TBC
Bharadwaj Consumer Products Ltd | Confidential - Steering Committee Distribution Only
11
Notes: This slide is deliberately the appendix-style one, it carries everything that did not fit cleanly onto the earlier slides. Do not read it line by line on the call, use it only if someone asks a specific question and you need the detail in front of you.
If Rajeev flips past this quickly, let him, it is here for completeness and for the minutes, not for airtime. Basically a backstop slide.

## Slide 12
UAT Readiness - October
• UAT window: October 2026, concluding ahead of the 7-8 November cutover weekend.
• Exact slot schedule and the tester roster are being circulated by Sneha's team next week.
• Tester nominations across Finance, Sales Ops and BI: TBC.
• All nine confirmed dashboards will be covered in the UAT script set, including the two reinstated ones.
• UAT environment is refreshed from production, so despatch data across plants will be current as of the refresh date.
• Float in the plan is limited. Not a lot of room if the October window slips.
Bharadwaj Consumer Products Ltd | Confidential - Steering Committee Distribution Only
12
Notes: Do not give exact UAT start/end dates on this slide, they are not finalised for circulation yet, Sneha is sending the slot schedule out next week, only after that should firm dates go into any written pack. If someone asks for the exact dates today, say they are coming in writing shortly, do not guess a number out loud.
Vikram will likely raise that Baddi and Nashik numbers were missing from his last extract - tell him it will be checked with Farida's team, do not attempt to resolve it live.
If asked how much float is really in the plan: not much, and it is better to say that plainly than to imply otherwise. This is the honest answer if Shalini or Marijke pushes on it.

## Slide 13
Asks of the Steering Committee
• Hold the 12-November go-live date. No further replanning around it from this point.
• Confirm the Phase 2 budget line covers the D04 and D11 build through to go-live, as communicated by the Group.
• Business (Finance / Sales Ops) to confirm UAT tester nominations for the October window within the next week.
• Group Finance to name an owner for resolving VAR-005 (credit notes), separate from Shalini as the variance owner, ahead of the 31-Dec Klarissen year end.
• Confirm the variance register position is carried into the Group audit file, not only the internal tracker.
• Approve.
Bharadwaj Consumer Products Ltd | Confidential - Steering Committee Distribution Only
13
Notes: The last bullet is intentionally short, it is the summary ask behind all the others: does this committee approve the plan as presented. Do not skip it just because it looks like a placeholder, Rajeev likes a clean close and will read it out as written.
If Marijke asks again 'so what is the plan' on VAR-005 after this slide, repeat: an owner and options come back before the next steering committee, not a fix date today.

## Slide 14
Next Steps and Actions
ID | Action | Owner | Due
AI-56 | Recirculate the plan with the cutover weekend and go-live date marked up (includes the master data freeze note). | Ananya Krishnan | 24-Sep-2026
AI-57 | Circulate UAT slots and the tester allocation. | Sneha Pillai | 28-Sep-2026
AI-58 | Revert to Group Finance on VAR-005 with a recommendation and a named owner. | Shalini Iyer / Ananya Krishnan | Before next steerco
AI-59 | Send the FY26 variance walk by month, in EUR at 92.40, to Wei Lin. | Ananya Krishnan | 02-Oct-2026
AI-60 | Confirm the variance register position is reflected in the audit file. | Rajeev Menon | 09-Oct-2026
AI-61 | Correct the rounding inconsistency between the tracker's summary and detail sheets. | Ananya Krishnan | 25-Sep-2026
 | Note: Shalini has not agreed November UAT resourcing; carried as an open item, not an action with a due date. |  | 
Bharadwaj Consumer Products Ltd | Confidential - Steering Committee Distribution Only
14
Notes: Six actions read back on the call by Sneha, plus the freeze note which got folded under AI-56 after the fact (it was raised informally mid-discussion and almost got lost, Ananya caught it and asked Sneha to add it).
Do not create a seperate action for the November resourcing gap, Shalini specifically asked for it to sit in the body of the minutes as a flag, not as a numbered action with her name against a date she has not agreed to.

## Slide 15
SYNTHETIC — generated for internal demo. No real entity depicted.