## Register
Project Drishti ¦ Variance Tracker ¦ v7 ¦ Northlane Analytics
ID | Title | Description | Root Cause | Impact (INR) | Owner | Status | Raised | Target Close | Actual Close | Comments
VAR-001 | FY26 Q1 revenue overstated | Cancelled / logically-deleted invoice lines were being counted as revenue in the Apr-Jun 25 numbers. Came up during the March findings session, Shalini would not sign the pack. | MAP_FACT_INVOICE_LINE had no DELETE_FLAG filter at all - every line incl. cancelled ones was loading. Corrected predicate NVL(DELETE_FLAG,'N')='N'. Deployed under CHG0021184. | 42163910 | Farida Contractor | Closed | 24/03/2026 | 31-May-26 | 12-Jun-2026 | fix confirmed live, Shalini ties out to TB now for Apr-Jun. as discussed on the finance call closing this one. -Ananya
VAR-002 | Month-end boundary drift | DATE_KEY was keying off a UTC timestamp instead of the IST invoice date, invoices near midnight on month end fell into the wrong month. | DATE_KEY derived from INVOICE_HEADER.CREATED_TS (written in UTC) instead of INVOICE_DT (IST). Invoices raised after 18:30 IST on the last day of a month landed in the next month. Fixed under ADR-005 and CHG0021207. | 8974200 | Karthik Subramanian | Closed | 24-Mar-26 | 31/05/2026 | 12/06/2026 | closed per Karthik. pls confirm no repeat in the Aug close ?? Sneha to check with Shalini before we report this as fully done
VAR-003 | Scheme discount double-count | Same set of invoice lines appear to be picking up the scheme discount more than once in some months. Flagged in the March findings session, dbl link theory from that meeting did not hold up. | Root cause is source-side, not in the ETL - a finance procedure in ORION rewrites the scheme discount amount. See the stored procedure walkthrough (Ani/Karthik) for the detail. Fix is a key-based merge rebuild of MAP_FACT_INVOICE_LINE, ADR-004, planned R2026.09. | 16890000 | Aniruddh Deshpande | Open | 24-Mar-2026 | 30-Sep-26 |  | ani still owns diagnosis, build with karthik's team. dont close this till R2026.09 actually ships, pls
VAR-004 | Duplicate facts on distributor reassignment | A distributor territory reassignment leaves two dimension rows both marked current, so the fact table joins twice and revenue doubles for that customer. Worked example DIST-W-0241 Mahalaxmi Distributors. | On a territory reassignment the closing DIM_CUSTOMER row's EFF_END_DT is set to the same timestamp as the new row's EFF_START_DT and CURRENT_FLG stays 'Y' on both. 61 customers have overlapping effective dates, 18 carry two current rows. | 6480500 | F. Contractor | Open | 19/05/2026 | TBC |  | Ishaan looking into the DIM_CUSTOMER fix with Karthik, worked example is DIST-W-0241. no target date yet, pls confirm with Ani if this needs a hotfix or goes in the phase 2 build
VAR-005 | Credit notes absent from warehouse | Revenue-affecting credit notes are not reflected in the reported EDW revenue line. Came up during the April close reconciliation. | Root cause with data architecture, being written up separately - not to be repeated on this sheet, pls confirm w Karthik before quoting. | 31120000 | Shalini Iyer | Open | 24-Apr-26 | TBC |  | impact validated by shalini against the trial balance, see VAR-005_detail tab. ?? need to check if this already reflects Aug or only till Jul, confirm before steerco pack goes out
VAR-006 | GST rate change mishandled | The Chandanaa HSN 3401 rate change was applied to the wrong period because the tax table has no effective dating. Found during the DQ assessment. | BCPL_EDW.TAX_RATE_MASTER is a truncate-and-reload snapshot with no effective dating. The 18% to 12% change effective 01-Oct-2025 was applied retrospectively to Apr-Sep 2025. Replaced by DIM_TAX_RATE under CHG0021339. | 3960000 | Neha Gokhale | Closed | 18/06/2026 | 31-Aug-26 | 28-Aug-2026 | DIM_TAX_RATE live, marking closed. honestly still waiting on someone to confirm the Sep invoices are picking the new rate correctly, dont think we have actually tested that yet tbh
VAR-007 | Late-arriving SKUs to UNKNOWN member | A SKU invoiced before the product dimension has seen it lands on the UNKNOWN member and never gets re-pointed once the dimension catches up. | No late-arriving dimension handling in MAP_FACT_INVOICE_LINE. Average 8,140 lines a month, peak 11,902 in Jan-2026, 2.0% of invoiced volume. Fails DQ-R-04 at 98.0% against a 99.5% threshold. | 2.0% of invoiced volume (no INR figure assigned) | Ritwik Ghosh | Open | 18-Jun-26 |  |  | half the readout we argued about whose backlog this actually sits in, dashboard team vs data team. no fix planned this release far as i know
VAR-008 | Feb duplicate load | The Sat 14-Feb load failed and was resubmitted manually, the whole night's invoice lines got appended a second time. Sat in the Feb numbers for three weeks before anyone caught it. | LP_DAILY_SALES resubmitted manually after a failure on 14-Feb-2026 as session SESS_884012, IKM Oracle Control Append appended the whole night again. Batch-id guard added in R2026.07. | 29410000 | Farida C. | Closed | 06/03/2026 | 31-Mar-26 | 02-Apr-2026 | closed, batch id guard tested on two month ends since with no repeat. Farida confirmed in the June sync
SYNTHETIC — generated for internal demo. No real entity depicted.

## VAR-005_detail
VAR-005 - Credit Note Impact Detail (validated 21-Jul-2026)
Month | CN Type | Doc Count | Amount (INR) | Notes
Apr-25 | RATE_DIFF | 58 | 1493540
Apr-25 | OFF_INV_ADJ | 40 | 1026470
May-25 | RATE_DIFF | 69 | 1775430
May-25 | OFF_INV_ADJ | 41 | 1045420
Jun-25 | RATE_DIFF | 34 | 879150
Jun-25 | OFF_INV_ADJ | 49 | 1274990
Jul-25 | RATE_DIFF | 71 | 1826980
Jul-25 | OFF_INV_ADJ | 37 | 961060
Aug-25 | RATE_DIFF | 57 | 1469500
Aug-25 | OFF_INV_ADJ | 65 | 1668300
Sep-25 | RATE_DIFF | 35 | 900620
Sep-25 | OFF_INV_ADJ | 75 | 1947580
Oct-25 | RATE_DIFF | 51 | 1317290
Oct-25 | OFF_INV_ADJ | 36 | 927340
Nov-25 | RATE_DIFF | 40 | 1023460
Nov-25 | OFF_INV_ADJ | 50 | 1278570
Dec-25 | RATE_DIFF | 45 | 1171360
Dec-25 | OFF_INV_ADJ | 79 | 2036890
Jan-26 | RATE_DIFF | 57 | 1475150
Jan-26 | OFF_INV_ADJ | 35 | 898420 | manual adjustment - refund processed outside system, see note
Feb-26 | RATE_DIFF | 35 | 910730
Feb-26 | OFF_INV_ADJ | 49 | 1259130
Mar-26 | RATE_DIFF | 36 | 931520
Mar-26 | OFF_INV_ADJ | 62 | 1621100
Total |  |  |  | validated by Shalini Iyer against FY26 trial balance, 21-Jul-2026
Note on E22: refund went to the distributor a/c XXXXXXXX4417, IFSC XXXX0000000 - do not circulate outside finance

## Log
Change Log (append-only - do not delete old rows)
Date | Entry
24/03/2026 | VAR-001, VAR-002, VAR-003 raised from T-03 findings. added to tracker.
06-Mar-26 | VAR-008 raised - Feb duplicate load, Farida investigating the re-run
02/04/2026 | VAR-008 closed. batch id guard added, tested ok
19/05/2026 | VAR-004 raised - distributor reassignment causing dup facts, worked eg DIST-W-0241
24-Apr-26 | VAR-005 raised - credit notes gap flagged by Shalini during April close
12-Jun-26 | VAR-001 and VAR-002 fixes deployed (CHG0021184, CHG0021207). closing both.
18/06/2026 | VAR-006, VAR-007 added from DQ assessment readout with Neha
21/07/2026 | VAR-005 impact figure updated after validation against TB. supersedes earlier estimate.
28-Aug-26 | VAR-006 closed - DIM_TAX_RATE live
02/09/2026 | chased Ani and Karthik again for a target date on VAR-003, still TBC
18-Sep-26 | tracker refreshed for steerco pack, this is v7. pls do not send v6 around, it is stale

## Summary
Variance Summary - as of 18-Sep-2026 (v7)
Status counts
Status | Count (live formula) | Count (reported to steerco)
Closed |  | 4
Open |  | 5
Total
counts in col C are from the last circulated draft, not reconciled to Register this week
Impact totals
Category | Reported (Cr) | Register sum (INR, live)
Closed | 8.4
Open | 5.45
Total | 13.85
note: reported column is what went in the steerco pack, rounded per variance to 2 decimals. live sum pulls the exact rupee figures off Register incl VAR-005 at 3.11 Cr, so it will not tie exactly to the reported 13.85 - this is normal, do not try to force it, ask Shalini if unsure
Note on C6: check with Ananya - I count 4 open on the Register tab now, not 5. left as-is from last week's draft, need to reconcile before this goes out again - Sneha